## WORK PLAN FOR WMO RA II PILOT PROJECT ON PUBLIC-PRIVATE ENGAGEMENT FOR SMART METEOROLOGICAL SERVICES IN MEGA-CITIES (PPE-SMSC)

- Introduction

Both the Geneva Declaration 2019 and the World Meteorological Organization (WMO) Guidelines for Public-private Engagement (PPE) place much emphasis on the actions to facilitate proactive PPE at regional and national levels. The WMO Regional Association II (RA II) Pilot Project on PPE for Smart Meteorological Services in Mega-cities (PPE-SMSC) is co-hosted by China Meteorological Administration (CMA), Hong Kong Observatory (HKO) and Macao Meteorological and Geophysical Bureau (SMG), under the guidance and coordination of PPE Office (PPEO) and Regional Office for Asia and the South-West Pacific (RAP) of WMO Secretariat. The project aims at exploring the PPE model in developing integrated urban meteorological services. The project proposal had been presented and discussed at the sixteenth session of the RA II Management Group (RA II MG-16) and at Seventeenth Session of RA II (RA II-17) (Phase I) and approved as a RA II pilot project (RA II-17-J-PP-1) at the RA II-17 (Phase II). This is the first regional pilot project on PPE among all regions.

- The relevant strategic objectives, resolutions and decisions to which the pilot project intends to contribute

2.1	The WMO Strategic Plan 2020–2023 (WMO-No. 1225), in its Objective 1.4, puts focus on designing and implementing new weather and water prediction services for the specific needs of Mega-cities and other urban areas, as well as on establishing principles and guidance for successful Public-Private Engagement (PPE), and facilitating a continuous dialogue between players and stakeholders based on collaboration and mutual reinforcement.

2.2	Resolution 80 (Cg-18) – Geneva Declaration 2019: Building Community for Weather, Climate and Water Actions, welcomes the engagement of all sectors in addressing the societal needs through weather, climate, water and other environmental information and services.

2.3	Resolution 11 (EC-72) – Guidelines for Public-Private Engagement (Edition 2020) requests the Presidents of the Regional Associations to give due consideration to the Guidelines in planning relevant regional activities, in particular those for raising mutual awareness and building trust between sectors, and in utilizing the potential of PPE in bridging the capacity gap, also encourage members to use the Guidelines in establishing collaboration and partnerships at the national level across public, private, academic and civil society sectors that pursue the common goals for the public good.

2.4	Resolution 32 (Cg-18) – Advancing Integrated Urban Services, decides to integrate the research-to-services value chain, that is science-based and services-driven, to support very high-resolution forecasting, predictions and warning systems to address the requirements of urban stakeholders.

2.5	Decision 2 (EC-71) – Good Practices for Implementation of Integrated Urban Services, encourages Regional Associations and Members to utilize the methodology and practices outlined in the “Guidance on Integrated Urban Hydrometeorological, Climate and Environment Services” to undertake pilot projects.

2.6	RA II priorities for 2020–2023, updated by the Joint Management Group Meeting for Asia and the South-West Pacific held in Singapore, from 29 to 31 October 2019 – The Group agreed to include impact-based forecasting and warning services – formulate concrete requirements for availability of data to improve forecast quality; pilot projects for urban services and mega-cities as one of the priority areas.

- Background and Purpose of the pilot project

3.1	As the urban population continues to grow, urban environment issues arising from weather, climate and water-related hazards as well as air pollution are becoming more prominent. City dwellers will be more vulnerable to natural hazards and disasters.

3.2	The development of an integrated urban service can address multiple challenges, including those related to Disaster Risk Reduction (DRR) with focus on the high impact weather in relation to dense population, and complex urban environment and structures. There are many gaps to fill in order to develop the relevant and efficient urban services, many of which need to be addressed in a multi-stakeholder approach. These gaps include, among others, the inadequacy of observing network to meet the needs for high-resolution weather services on one hand and the growing availability of massive non-conventional data generated by non-NMHSs stakeholders on the other; the very limited research to drive the development of higher-resolution (sub-kilometre) models; and the lack of innovative technology (such as artificial intelligence and machine learning) to process the massive data for the purpose of better understanding the impacts of weather events and integrating the weather forecast information into decision makings related to urban development and management. To deal with those challenges, it is essential to engage stakeholders from public, private and academic sectors to share observation, to develop innovative solutions, and to generate high-quality information and services.

3.3	Guangdong-Hong Kong-Macao Greater Bay Area (GBA) is one of the world’s largest urban zones with the highest density of population, vehicles and economic output. Dense population and highly built-up areas are highly vulnerable to natural hazards. The city dwellers’ daily life, and the social and economic development are highly sensitive to severe weather events. These characteristics are typical of the fast-growing urban areas in Asia and the Pacific. At the same time, GBA has also a hub for IT companies, universities and research institutes, and commercial weather and climate information service providers. The pilot project to be implemented in this area will be collaborated among government agencies, private businesses and the academic community, capitalizing on the existing sophisticated observing network and forecasting and warning capacity of meteorological offices, the inter-agency coordination mechanism of the municipal government, as well as the research and innovation capacity of local IT companies and academic institutes. The purpose is to explore an effective PPE mechanism which will enable the development of open data facility, open platform for developing innovative urban services, common standards, and impact-based forecast and risk-based warning services contributed by multi-stakeholders.

### 4.	Main Objectives of the pilot project

The objectives to be achieved by 2024 are:

4.1	To establish a sustainable model of meteorological data acquisition and sharing with wide participation of public, private and academic stakeholders, to promote the effective use of multi-source data, and to improve the sharing of regional grid-based meteorological products.

4.2	To engage all sectors, communities, and citizens to establish an agreed set of urban safety development indicator, and to develop the impact-based disaster risk early warning service for decision support.

4.3	To develop targeted early warning and communication technologies through cooperation with partners from private companies and academia, and to provide user-interactive and demand-driven early warning information for decision makers.

4.4	To carry out urban climate impact assessment in collaboration with other government departments, and academic institutions (i.e. institutes and universities with expertise and research on urban planning and design).

4.5	To develop risk-based storm surge forecast service for vulnerable coastal areas through collaboration with relevant government departments and community organizations/groups.

4.6	To optimize flood service to improve the effectiveness of disaster prevention and mitigation through collaboration with the urban utility companies, community and other stakeholders.

4.7	To develop scalable practices and mechanisms related to effective PPE model for smart meteorological services in mega-cities.

### 5.	Project Organization Structure

A three-tier organizational structure has been set up for coordinating and implementing the pilot project. The following are the terms of references of the Scientific Advisory Committee (SAC), the Project Coordination Group (PCG) and the Project Working Group (PWG).

5.1	Scientific Advisory Committee (SAC)

Terms of Reference:

Mainly responsible for providing scientific and technical guidance for project, consulting on project implementation process, supervising and periodical evaluation and acceptance of pilot project, and paying special attention to the following issues:

- To be responsible for guiding the implementation of the project in accordance with WMO standards and best practices in terms of data exchange, risk warning, climate services, public-private participation mechanism construction, integrated urban services and other related contents.

- Continue to monitor the implementation of the pilot project, including reviewing the progress report submitted by the project working group and providing comments, and attending the pilot project meetings.

- (iii) To evaluate the best practices in the implementation of the project scientifically and recommend typical and exemplary project results to the relevant technical committee for upgrading into WMO technical specifications, standards or best practices.

Membership:

Composition of Scientific Advisory Committee

| Membership | Name | Title | Specific guidance area |
| --- | --- | --- | --- |
| Co-Chair | Dr Feng LIANG | Co-Chair, Study Group on Integrated Urban Services/SERCOM | Urban Services |
| Co-Chair | Mr Pak Wai CHAN | Assistant Director, Hong Kong Observatory | Urban Services |
| Member | Mr Iu Man TANG | Vice Director, Macao Meteorological and Geophysical Bureau | Urban Services |
| Member | Mr Tatsuya Kimura | Director, Public-Private Engagement Office (PPEO) | PPE mechanism |
| Member | Mr Qingliang ZHOU | Chair of RA II WG Services | Urban Services |
| Member | Mr SATO Yoshiaki | Chair of RA II WG Infrastructure | Infrastructure |
| Member | Dr/Ms Kamaljit RAY | Vice chair of RA II WG Services | Urban Services |
| Member | Dr Mai Van KHIEM | RA II Regional Focal Point on Research | Urban Services |
| Member | Mr Alexander Baklanov | Expert, Atmospheric Environment Research Division, WMO Science and Innovation Department | Urban Services |
| Member | Dr Chao REN | Associate Professor, University of Hong Kong | Climate service |

5.2	Project Coordination Group (PCG)

Terms of Reference:

Mainly responsible for coordinating project implementation, coordinating among technical commissions of WMO, relevant expert groups, WMO Secretariat, project participants and partners, in terms of experts, technology and achievements promotion, especially playing a key role as the bridge between SAC and PWG. Also, responsible for reporting the project progress and results to the RA II Management Group.

Membership：

Composition of Project Coordination Group

| Membership | Name | Affiliation/Title |
| --- | --- | --- |
| Co-leader | Mr Ben Churchill | Head, Regional Office for Asia and the South-West Pacific (RAP) |
| Co-leader | Ms Mingmei LI | Senior Engagement Officer, PPEO |
| Member | Mr Jun YU | Regional Officer, RAP |
| Member | Ms Xiaodan NA | Department of International Cooperation, CMA |
| Member | TBC | Department of Disaster Mitigation, CMA |
| Member | Dr Haobo TAN-TBC | Vice-Director General, Guangdong Meteorological Service, CMA |
| Member | Ms Yanqing WANG | Director General, Shenzhen Meteorological Service |
| Member | Mr Xia MAO | Deputy Director General, Shenzhen Meteorological Service |
| Member | Mr Pak Wai CHAN | Assistant Director, Hong Kong Observatory |
| Member | Mr Iu Man TANG | Vice Director, Macao Meteorological and Geophysical Bureau |

## 5.3	Project Working Group (PWG)

Terms of References: responsible for the implementation of the pilot project and submit progress report to RA II Working Groups.

Membership：

Notes: Invitations to partners and PPE representatives (Enterprises, academia institutions, social organizations and communities) will remain open and membership  will be supplemented according to actual conditions during project implementation.

Composition of Project Working Group

| Membership | Name | Affiliation/Title |
| --- | --- | --- |
| Project Organizer | Dr/Ms Xiaolin WEI | Senior Engineer, Weather Warning and Forecasting Division, Shenzhen Meteorological Service, CMA |
|  | Mr Minghua LI | Vice head, Weather Warning and Forecasting Division, Shenzhen Meteorological Service, CMA |
|  | Mr Dunxun LIU | Senior Engineer, Planning and Development Division, Shenzhen Meteorological Service, CMA |
|  | Ms Shuting ZHANG | Engineer, Weather Warning and Forecasting Division, Shenzhen Meteorological Service, CMA |
|  | Mr Wai KONG | Senior Scientific Officer, High Impact Weather Team，Hong Kong Observatory |
|  | Mr Chan Wa LOK | Chief of Meteorological Monitoring Center, Macao Meteorological and Geophysical Bureau |
|  | Mr Man Chi WONG | Technician, Macao Meteorological and Geophysical Bureau |
| Partners and PPE representatives | Dr Yuanfu XIEl | Chief Scientist, Guangdong-Hong Kong-Macao Greater Bay Area Weather Research Center for Monitoring Warning and Forecasting |
|  | Ms Lu YU | Chief Engineer, Urban Planning and Design Institute of Shenzhen |
|  | TBC | University representative |
| Third Party Evaluation | TBC | To be responsible for the evaluation of social and economic benefits |

## 6.	Proposed Implementation Activities and Timeline

| No. | Activity | Timeline |
| --- | --- | --- |
| 1. Pilot project consultation |  |  |
| 1.1 | To organize a coordination meeting by PWG (Completed) | 2021 |
| 1.2 | To organize a preparatory meeting by PWG (Completed) | Dec 2021 |
| 1.3 | To set up a complete project organizational system by PWG (Completed) | Jan 2022 |
| 1.4 | To organize a Kick off meeting by PWG | Feb 2022 |
| 2. Pilot Project implementation phase |  |  |
| 2.1 | Open for multi-stakeholders, and encourage participation of high-tech enterprises and academic institutions in the region by PWG | During the entire project |
| 2.2 | Open to RA II Members, welcome interested RA II Members proactive in their support and participate in the project, and to actively share, promote, and communicate with RA II Members with the outcome of the Pilot Project. coordinated by PCG | During the entire project |
| 2.3 | To submit progress report to Working Groups of RA II by PWG | Every half year |
| 2.4 | To organize a mid-term evaluation meeting, report to SAC and PCG by PWG | Early 2023 |
| 2.5 | Report progress of the pilot project to RA II MG by PCG | 2023 |
| 2.6 | To organize a review meeting, report to SAC and PCG by PWG | 2024 |
| 2.7 | To submit final report of the pilot project to RA II MG by PCG | 2024 |
| 3. Communication and outreach |  |  |
| 3.1 | Distribute newsletters to interested Members, or provide working packages for download by PWG, coordinated by PCG | Update when necessary |
| 3.2 | Organize an International Workshop by PWG | First half of 2023 |

## 7.	Proposed Implementation Objectives and plan

IMPLEMENTATION OBJECTIVES

| No. | Objective title | Objective Coordinator(s) |
| --- | --- | --- |
| I | Real-time sharing of gridded meteorological product | CMA (China) |
| II | To develop impact- and risk-based disaster risk warning services | CMA (China) |
| III | To develop a targeted information distribution system | CMA (China) |
| IV | To collaborate with partners to develop urban climate impact assessment | CMA (China) |
| V | To develop risk-based storm surge forecast service for vulnerable coastal areas | HKO (Hong Kong, China) |
| VI | To optimize flooding alert service to improve the effectiveness of disaster prevention and mitigation | SMG (Macao, China) |
| VII | To summarize the PPE model of Smart Meteorological Service Community in Mega-cities | Mainly by CMA (China), with engagement of HKO (Hong Kong, China) and SMG (Macao, China) |

*Note: Under the guidance of CMA and Guangdong Meteorological Service, SZMC is responsible for the specific implementation of the pilot project.

Objective No. I

| Project Title | Real-time sharing of gridded meteorological product |
| --- | --- |
| Type | Regional Implementation Objective (RA II) |
| Timescale | 2021-2024 |
| Background | Consistent with Resolution 40 (Cg-12), WMO policy and practice for the exchange of meteorological and related data and products including guidelines on relationships in commercial meteorological activities, and Objective 2.1 of the WMO Strategic Plan 2020-2023, which encourages members to utilize observation systems operated by relevant government agencies, research entities, non-profit organizations and private companies, and non-traditional data accessing tools, such as using crowd-sourcing and the Internet of things to optimize access to Earth system observations are also encouraged, and set the key development goal of developing supplementary regulatory and guidance documents to promote the integration of external sources of observations in the WIGOS framework. Objective 1 will explore the sustainability models for the acquisition and exchange of meteorological product with broad participation of multi-stakeholders from the public, private and academic communities within the PPE policy framework, exploring a possible way to establish innovative cooperation models. |
| Plan/Activities | Objective 1 mainly include the following three aspects: (i) establish gridded-products; (ii) realizing real-time open sharing of meteorological grid product; and (iii) strengthen the service supervision. (i) establish gridded-products: - Based on the automatic meteorological stations deployed in Shenzhen, combining other data from multi-sectors, including other departments, enterprises, private and research institutions. For example, in order to solve the problem of insufficient observation at sea, jointly establish automatic meteorological observation stations on offshore oil platforms with oil mining companies, which will be beneficial for both sides through sharing data and product. In order to clearly depict the urban land surface, jointly establish the urban underlying information such as the height and density of tall buildings with Planning Bureau and social enterprises, and integrate the information into the data model. - Utilize the data assimilation technology, an urban climate gridded-product system will be established, consisting of 10-year historical data and real-time data at a horizontal resolution of 1 km and temporal resolution of 12 minutes at the initial stage of the project. Then efforts will be made to reach a horizontal resolution of 500m or less and temporal resolution of 6 minutes for 2024. (ii) realizing real-time open sharing of meteorological grid product: - Based on the computing, storage, telecommunication and security services available on the Smart City Cloud Computing Platform built by Shenzhen Municipality, an open platform for meteorological service innovation will be developed. - Establish an open innovation service carrier supporting both on-line and off-line data access and utilization. - Technical standards related to the data interface and service interface will be developed to enable real-time sharing of the gridded product. (iii) strengthen the service supervision: - Through establishing service quality management and performance rating systems, the partner service providers who access and use the open data will be subject to regular performance evaluation. The evaluation results will be used to improve service delivery and capability. |
| Aim(s) | - Processing multi-source observation data to generate gridded product system, use as open data for further development and sharing; - To promote the effective utilize of meteorological data from multi-sources in order to improve forecast, services and meteorological scientific research, improve the efficiency of exchange and utilization of meteorological data and extend the value chain of meteorological services; - Through the establishment of meteorological service quality system and credit management system, it is ensured that all processes of meteorological service are carried out under controlled. |
| Benefits | Members in RA II are available to the latest progress of the pilot project, data sets, specifications, standards and other documents formed during the implementation of the project will be shared with interested members as working packages. |
| Expected Key Deliverables | - Urban climate gridded-product system will be established. - Management standard of meteorological data collection will be established. Standardize the process of data sharing between government departments, meteorological data socialized collection, and jointly establish meteorological observation and sharing data. - Standard of data exchange and sharing will be established, including the establishment of data sharing channel, the construction of sharing platform, the establishment of data interface standard and the design of service interface, so as to promote the sharing and exchange of meteorological gridded products. - Meteorological service quality system and credit management system will be established, standardizing the process of meteorological data sharing and service. |
| Major risk(s) | Information security risk. It may receive viruses or other high-risk data files in the process of collecting social observation data, may resulting in an interruption of the server. |
| Project Coordinator | CMA (China) |

Objective No. II

| Project Title | To develop impact- and risk-based disaster risk warning services |
| --- | --- |
| Type | Regional Implementation Objective (RA II) |
| Timescale | 2021-2024 |
| Background | Corresponding to the call by Geneva Declaration 2019 on all governments to safeguard and strengthen the authoritative voice of NMHSs for the issuance of warnings and relevant information to support critical decisions related to natural hazards and disaster risks in collaboration with national disaster management authorities”, and WMO Guidelines on Multi-hazard Impact-based Forecast and Warning Services (WMO-No. 1150), objective 2 will develop impact- and risk-based disaster risk warning services to enhance the capacity of meteorological disasters management in cities or urban agglomerations, ensuring the safe development of cities. |
| Plan/Activities | Objective 2 mainly include the following two aspects: (i) to develop the fine impact- and risk-based early warning service for decision support, and (ii) to develop individualized and customized impact- and risk-based early warning and forecast service for users of meteorological disaster sensitive industries. (i) to develop the fine impact- and risk-based early warning service for decision support: - In accordance with needs in DRR-related decision making, inter-agency coordination and community response, general survey of meteorological disasters will be carried out jointly with social enterprises or individuals. Disaster management authority, neighbourhood managers, and the urban citizens will be engaged in developing and defining disaster-inducing threshold values. - Big data and AI will be applied to develop the technology for quantitative and objective analysis of weather conditions that trigger disasters with academic sectors. Recommendation algorithms based on tag association rules, and collaborative filtering will be employed. - Generate and deliver the personalized service products on demand, which is expected to improve impact-based forecast and risk-based warning services. (ii) to develop individualized and customized impact- and risk-based early warning and forecast service for users of meteorological disaster sensitive industries: - Weather-sensitive user sectors will be engaged in developing threshold values for quantitative risk assessment. The users will be able to adjust the threshold value in real-time manner. This interactive process will provide dynamic feedback on users’ real-time needs for the service content, formats and delivery means. - Develop threshold-based and customized forecast and warning services. |
| Aim(s) | Explore the use of PPE model to establish urban safety development index system, jointly develop the fine impact- and risk-based early warning service for decision support, and develop individualized and customized impact- and risk-based early warning and forecast service for users of meteorological disaster sensitive industries, improving urban resilience and urban disaster prevention capacity. |
| Benefits | Members in RA II are available to the latest progress of the pilot project, index system, service standards and other documents formed during the implementation of the project will be shared with interested members as working packages. Provide necessary support and assistance to members who are willing to apply the achievements locally. |
| Expected Key Deliverables | - A set of dynamic disaster threshold index system and corresponding management mechanism will be established in cooperation with the national disaster management authority. - A fined impact- and risk-based early warning service system for decision support will be developed. - Meteorological disaster service rules for sensitive industries (such as subway) in mega-cities will be established. |
| Major risk(s) | Limited by the technical level of weather forecast, the effect of impact- and risk-based early warning will be affected occasionally. |
| Project Coordinator | CMA (China) |

Objective No. III

| Project Title | To develop a targeted information distribution system |
| --- | --- |
| Type | Regional Implementation Objective (RA II) |
| Timescale | 2021-2024 |
| Background | In line with the WMO Strategy for service delivery (WMO-No.1129) and its implementation plan, strengthening the authoritative voice of NMHSs and promoting the guarantee of life safety, and the requirement of CMA to “enable the precise and prompt distribution of warning messages to the government decision-makers, the disaster risk managers of public agencies and private businesses, and the general public”, objective 3 will cooperate with relevant stakeholders to develop targeted early warning distribution technologies to provide user-centred, interactive and demand-driven early warning information to policymakers and the most vulnerable in key regions and critical periods, achieving accurate, rapid and widespread dissemination of early warning information for key time periods, key regions and vulnerable populations. |
| Plan/Activities | Objective 3 mainly include the following three aspects: (i) develop targeted impact-based disaster defense decision-making services; (ii)point-to-point precise calling services regarding severe weather under specific needs; and (iii) jointly develop user-centred interactive response services on-demand. (i) develop targeted impact-based disaster defence decision-making services: - Launch a collaborative research with telecommunication companies. - Develop precise targeted warning dissemination technology, and allow for the warning messages directed to high-risk areas such as densely populated areas, and areas vulnerable to water-logging and geological disasters. Through the labels of location, crowd characteristics and composition, data screening and cleaning are carried out to establish targeted impact-based disaster defence decision-making services. - Warning messages will be issued for specific group of people, communities and scenarios by automatically pushing warning information to mobile phone users who enter the high-risk areas that are identified before-hand on the basis of weather information. (ii) point-to-point precise calling services regarding severe weather under specific needs: - Refined weather forecasts and warnings will be tailored to the needs of specific populations and communities in imminent danger of severe weather events. For example, “Alarming Bell” warning service, which is designed to prepare students and their parents for school days impacted by typhoons or rainstorms. - Connect to city operation centre, enabling point-to-point calling services regarding severe weather hazards, in response to the specific needs of emergency management directors in government agencies and the highly weather-sensitive sectors. (iii) jointly develop user-centred interactive response services on-demand: New technology will be employed to develop a new model of intelligent service, perceive and match user needs, form precision service model, transform complex meteorological data into personalized product that users can easily understand, and realize meteorological situational intelligent service through user portrait, improving meteorological fine service. |
| Aim(s) | Improve the early warning release system, improve the timeliness, coverage and accuracy of meteorological disaster early warning release. Enable the precise, prompt and wide distribution of warning information directed to the vulnerable groups in critical areas and at critical periods. |
| Benefits | Members in RA II are available to the latest progress of the pilot project, the service standards and service mechanisms for targeted early warning release, an intelligent gridded meteorological service model in mega-cities will be shared with interested members as working packages. |
| Expected Key Deliverables | - Service standards and service mechanisms for targeted early warning release will be established. - A set of technical standards for the accurate release of early warning information which is easy to promote will be established. - An intelligent gridded meteorological service model in mega-cities, which is based on automatic user demand perception, interactive customization, and society participation will be developed. |
| Major risk(s) | Differences in management policies for telecommunication operators in different countries and regions may affect the applicability. |
| Project Coordinator | CMA (China) |

Objective No. IV

| Project Title | To collaborate with partners to develop urban climate impact assessment |
| --- | --- |
| Type | Regional Implementation Objective (RA II) |
| Timescale | 2021-2024 |
| Background | In response to requirements and calls in a few guiding documents at different levels, including the importance placed by the WMO Vision for 2030 on “underpinning the sustainable development through best possible services”; the call by the Geneva Declaration 2019 to all partners for “optimizing national adaptation planning and disaster risk management to build resilience at all levels through a greater involvement of the expertise of the NMHSs in partnership with other public institutions, private and academic sectors, as well as civil society”; the requirement by CMA to “strengthen service capabilities to support decisions in climate change impact assessment, management and adaptation for the purpose of environment and climate security”; and the task of “building a climate-resilient city” specified in the Outline Plan on Leading the Development of An Epitome of Beautiful China (2020–2035) issued by Shenzhen Municipal Government. Objective 3 will collaborate with other departments, academic institutions (urban planning and design institutes, universities) to conduct urban climate impact assessments to support sustainable development and improve urban resilience. |
| Plan/Activities | Objective 4 mainly include the following three aspects: (i) cooperate to establish a “planning + meteorological” PPE service mechanism; (ii) cooperate to establish an “ecological + meteorological” PPE service mechanism; and (iii) cooperate to establish a “water + meteorological” PPE service mechanism. (i) cooperate to establish a "planning + meteorological" PPE service mechanism: - Cooperation mechanisms, management methods and evaluation methods will be established in cooperation with the Municipal Planning Bureau and academic institutions. - Collaborative assessments on the city’s status of natural ventilation will be carried out around the impact of urban development on local climate and environment, so as to realize the service of climate-leading urban refined development planning. (ii) cooperate to establish an “ecological + meteorological” PPE service mechanism: - Collaborative researches with ecological authority, academic institutions and enterprises will be carried out to explore a mechanism to track, monitor and manage urban climate. - Develop the “ecological + meteorological” PPE service mechanism. - Develop the tracking, monitoring and service mechanism of urban ecological climate, ensuring the city to be more liveable and pleasant to visit. (iii) cooperate to establish a “water + meteorological” PPE service mechanism: - Cooperate with Municipal Water Bureau and relevant enterprises to carry out research on rainfall law in high-density cities based on the high-resolution urban observation data. - Develop multi-source and multi-scale assessment technology for urban heat island. - Serve the construction of spongy city by provide technical specifications. |
| Aim(s) | Cooperate with other government departments, academic institutions (urban planning and design institute, university) to carry out urban climate impact assessment, realize the service of climate-leading urban fine development planning, support urban sustainable development, improve urban resilience, and serve sponge city construction. |
| Benefits | Members in RA II are available to the latest progress of the pilot project, climate service model for mega-cities and urban agglomerations will be shared with interested members as working packages. |
| Expected Key Deliverables | Easily promoted climate service model for mega-cities and urban agglomerations. |
| Major risk(s) | Under the influence of climate difference between countries and regions, service models may be limited in the process of popularization and application. |
| Project Coordinator | CMA (China) |

Objective No. V

| Project Title | To develop risk-based storm surge forecast service for vulnerable coastal areas |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Timescale | 2021-2024 |
| Background | Tropical cyclones are one of the major hazardous weather frequently encountered in RA II. Extreme storm surges brought by tropical cyclones can bring extensive inundation to low-lying coastal areas resulting in significant casualties and damages to coastal infrastructures. |
| Plan/Activities | A specific application of risk-based storm surge forecast service for the vulnerable coastal areas in Hong Kong will be developed by the Hong Kong Observatory (HKO). To formulate such risk-based storm surge forecast service, a probabilistic storm surge prediction system will be developed: (i) By applying ensemble prediction strategies, the probabilities of possible storm surge scenarios for vulnerable coastal areas will be computed, along with various inundation risk assessment products. The weather forecasters and emergency management units can make reference to the information and initiate emergency response actions. (ii) In order to provide better risk assessment services for the emergency response management of the vulnerable coastal areas, there is a need to collaborate with relevant government departments and community organizations/groups to evaluate the vulnerabilities of the coastal areas to storm surge inundation taking into account their operational experience. |
| Aim(s) | Develop a risk-based storm surge forecast service for vulnerable coastal areas in Hong Kong based on numerical storm surge modelling and the probabilistic outputs of the ensemble prediction systems (EPS). Showcase the effectiveness of the risk-based forecast service, formulated under the collaboration with relevant stakeholders, in the early alerting of the storm surge threats to the coastal communities. |
| Benefits | - The risk-based storm surge forecast service developed under this project is expected to help the weather forecasters and emergency management units make better-informed decisions in preparing the low-lying coastal areas for the impending threats of storm surge, particularly in association with those potential extreme events that may not be accurately depicted by the deterministic forecasts with a lead time longer than one day or so. - Through the documentation of methodologies and sharing of HKO’s experiences in developing the risk-based storm surge forecast service under this project, RA II Members who may face similar risks of extreme storm surges brought by tropical cyclones will hopefully benefit from the project as a reference for establishing and operating similar services in their countries. |
| Achievements in the previous period (2019-2020) | A prototype of risk-based storm surge forecast products has been developed for trial use by the HKO’s weather forecasters based on probabilistic prediction generated using past error statistics. Preliminary study has also been conducted to develop and test relevant methodologies to post-processing the outputs from EPS. |
| Expected Key Deliverables | - Project report for reference by RA II members who may face similar risks of storm surge brought by tropical cyclones. - Experience sharing in the International Workshop on Smart Meteorological Services for mega-cities in Asia in 2023. - If appropriate, to be included as a case study for the implementation of impact-based forecast services on the future companion webpage of the WMO Guidelines on hazard Impact-based Forecast and Warning Services (WMO No. 1150). |
| Major risk(s) | - Performance of EPS forecasts. - Lack of past data/reports to facilitate the impact study of storm surge for individual coastal areas as the vulnerabilities of different areas to storm surge inundation could be very different and localised. - Lack of response from stakeholders and their participation in formulating the risk-based forecast service. |
| Project Coordinator | HKO (Hong Kong, China) |

Objective No.VI

| Project Title | To optimize flooding alert service to improve the effectiveness of disaster prevention and mitigation |
| --- | --- |
| Type | Regional Implementation Project (RA II) |
| Timescale | 2021-2024 |
| Background | In the low-lying areas near the inner harbour of Macao, flooding occurs every year due to astronomical tides or rainstorms, which results in traffic diversions and affects citizen’s travel. Moreover, if the astronomical tide coincides with the storm surge brought by tropical cyclone, their combined influence may cause widespread severe flooding, which will result in huge casualties and damage in properties. |
| Plan/Activities | Macao Meteorological and Geophysical Bureau plans to introduce the storm surge ensemble forecast technique and to improve the forecast competency of flood along with storm surge warning and rainstorm warning. In addition, the bureau will optimize the flooding alert service by providing the latest forecast and real-time flood information automatically. |
| Aim(s) | - Achieve the goal to provide smart flooding alert by combining real-time flood information from our monitoring network and our ensemble forecast data. - Achieve the goal to provide smart flooding service by collaboration with the utilities, community and private sector by means of utilizing the smart flooding alert mentioned above. |
| Benefits | RA II Members are kept informed of the progresses. |
| Expected Key Deliverables | - Continue to optimize the tide and land water level monitoring network and coordinate with the issuance of storm surge warning and rainstorm warning, the forecast and real-time flood information will be automatically sent via different electronic channels in order to allow relevant government departments, utilities, social groups and residents to take timely preventive measures and response. (e.g. taking different routes, clearance of sewers, closing the parking lot, evacuation and shutdown of power supply, etc.) - Continue to increase and promote the use of flood elevation marking sticker, where the public and the disaster prevention department can more easily understand the possible scope and extent of the damage caused by floods. This will also improve the effectiveness of storm surge warning, rainstorm warning and the flooding alert service. |
| Major risk(s) | Lack of responses from some RA II Members focal points. |
| Project Coordinator | SMG (Macao, China) |

Objective No. VII

| Project Title | To summarize the PPE model of Smart Meteorological Service Community in Mega-cities |
| --- | --- |
| Type | Regional Implementation Objective (RA II) |
| Timescale | 2021-2024 |
| Background | Objective 1.4 of WMO Strategic Plan 2020-2023 focus establishing principles and guidance for successful public-private engagement, and facilitating a continuous dialogue between players and stakeholders based on collaboration and mutual reinforcement. Accordingly, resolution 11 of Guidelines for Public-Private Engagement (EDITION 2020), which has been adopted in EC - 72, requests the presidents of the regional associations to give due consideration to the Guidelines in planning relevant regional activities, in particular those for raising mutual awareness and building trust between sectors, and in utilizing the potential of public-private engagement in bridging the capacity gap, and encourages Members to use the Guidelines in establishing collaboration and partnerships at the national level across public, private, academic and civil society sectors that pursue the common goals for the public good. Therefore, the pilot project implementation will follow WMO guidelines on PPE, establish mechanisms of engaging multiple stakeholders to improve smart meteorological services, ensuring objective 1 to 6 to be realized. |
| Plan/Activities | Objective 7 mainly summarize the following three mechanisms: - mechanisms and business models to increase the collection and sharing of data and products between stakeholders: Stakeholders will participate in the establishment of standards and mechanisms for collecting and sharing meteorological data, and carry out overall planning for data sharing, social meteorological data collection and co-construction and sharing observation data between government departments, so as to absorb and collect observation data from other government departments, enterprises, private and research institutions, promoting data sharing and exchange between government departments, enterprises, private and research institutions, and improving the efficiency of meteorological data exchange and utilization. To establish a data service model of "All for One and One for All". (ii) mechanism to engage multiple stakeholders in developing and providing innovative weather information and services delivery. (iii) mechanisms to engage multiple stakeholders in setting standards and recommending practices to ensure data and services quality, which are to be recognized and confirmed by all service providers: Explore the development of innovative data exchange mechanism to improve the availability of meteorological data and promote data sharing, improving the efficiency of data exchange and utilization, and extending the value chain of meteorological services. |
| Aim(s) | To fully understand and master meteorological and climate services demand of various industries and departments of the city by forming functional and mutually beneficial partnerships with other governmental sectors, academic institutions, the private sector and the public. To form an interdisciplinary scientific research mechanism integrating meteorological knowledge and knowledge in related fields with the advantage of science and technology enterprises and scientific research institutes, enhancing the capacity of meteorological and climate services to mega-cities and their sustainable development, and extending the value chain of relevant sectors to enhance their own capacity. To implement the latest policies on PPE proposed by WMO in the process of pilot project implementation, and accumulate experience and provide feedback. |
| Benefits | RA II Members are kept informed of the progresses, and the concerned information will be shared with RA II Members by reports. |
| Expected Key Deliverable | A summary report on the development of smart meteorological services in mega-cities using the PPE model. |
| Major risk(s) | Awareness differences for public private sectors and the uncertainty of partnerships may lead to adjustments in implementation. |
| Project Coordinator | Mainly by CMA (China), with engagement of HKO (Hong Kong, China) and SMG (Macao, China) |